## Sheet5
Assigned To | (All)
Row Labels | Sum of Progress (%)
Define Requirements | 0.4
High | 0.4
Design Mockups | 0.3
Medium | 0.3
Develop Homepage | 0.2
High | 0.2
QA Testing | 0.1
(blank) | 0.1
Grand Total | 1

## Sheet4
Sum of Progress (%) | Column Labels
Row Labels | In Progress | Not Started | Grand Total
Alice | 0.4 |  | 0.4
Bob |  | 0.3 | 0.3
Carol |  | 0.2 | 0.2
Dave |  | 0.1 | 0.1
Grand Total | 0.4 | 0.6 | 1

## Sheet1
project management tracker
Task id | Task name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Notes
1 | Define Requirements | Alice | 2024-01-11 | 2024-01-15 | In Progress | High | 40% | Initial draft complete
2 | Design Mockups | Bob | 2024-01-16 | 2024-01-20 | Not Started | Medium | 30% | Waiting for requirements
3 | Develop Homepage | Carol | 2024-01-21 | 2024-01-30 | Not Started | High | 20%
4 | QA Testing | Dave | 2024-02-01 | 2024-02-10 | Not Started | low | 10%
Step 1: Add Conditional Formatting for Visual Cues
Select the Progress (%) column.
Use formatting to highlight cells based on their status green
Task id | Task name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Notes
1 | Define Requirements | Alice | 2024-01-11 | 2024-01-15 | In Progress | High | 40% | Initial draft complete
2 | Design Mockups | Bob | 2024-01-16 | 2024-01-20 | Not Started | Medium | 30% | Waiting for requirements
3 | Develop Homepage | Carol | 2024-01-21 | 2024-01-30 | Not Started | High | 20%
4 | QA Testing | Dave | 2024-02-01 | 2024-02-10 | Not Started | low | 10%
step 2:-Due Date Alerts
Go to Conditional Formatting > New Rule > Use a formula to determine
Formula:-: =AND(G21>=DATE(2024,1,1), G212<=DATE(2024,2,1)).
Step:-3 find to assigned to,status and progrees(%) by pivot table
sheet:- 4
Step:-4 find to task name ,assigned to, priority and Progress (%) by pivot chart
Sheet:-5